# Project Charter: Online Learning Platform Launch

## Objective

Launch an online learning platform within 12 weeks and ₹8,00,000, and reach 2,000 registered sign-ups by the end of week 12. The platform goes live in week 9 with Six launch courses, leaving three weeks for acquisition and fixes.

## Scope

- Learning platform on a ready-made LMS: sign-up and login, course catalogue, video and quiz delivery, progress tracking, completion certificates

- Payment gateway (UPI and cards), ready for paid courses

- Six launch courses with videos, quizzes and notes

- Landing page, waitlist, and email, social and partner campaigns

- Help centre, basic support desk and an analytics dashboard

- Terms of use and privacy policy, including Indian data-protection requirements

## Out of scope

- Native iOS and Android apps (the launch is a mobile-friendly website)

- Live classes, cohorts and community features

- A marketplace for third-party instructors

- Multiple languages and enterprise (B2B) sales

- Building an LMS from scratch

- Content creation or marketing beyond week 12

## Milestones

| Week | Milestone | Gate |
| --- | --- | --- |
| 1 | Charter approved, team and vendors confirmed | Sponsor sign-off |
| 2–3 | LMS chosen, UX and course plan done | Platform and course list approved |
| 4–6 | Platform set up, payments integrated, first 3 courses produced | Working demo |
| 7 | All 6 courses uploaded, full testing | Zero critical bugs |
| 8 | Beta with 50 users, waitlist opens | Beta feedback fixed |
| 9 | Public go-live | Go/no-go review |
| 10–12 | Acquisition push, support, weekly reporting | 2,000 sign-ups |
| 12 | Closure review and handover | Final report accepted |

## Budget split

| Category | Amount (₹) | Share |
| --- | --- | --- |
| Platform and tech (LMS, hosting, payments) | 2,00,000 | 25% |
| Course content production | 2,00,000 | 25% |
| Marketing and sign-up campaigns | 2,00,000 | 25% |
| Design, QA and support contractors | 80,000 | 10% |
| Legal and compliance | 40,000 | 5% |
| Contingency | 80,000 | 10% |
| Total | 8,00,000 | 100% |

## Success metrics

- 2,000 registered sign-ups by the end of week 12

- At least 40% of sign-ups enrol in a course within 14 days

- Total spend within ₹8,00,000, at or below ₹400 per sign-up

- Go-live by the end of week 9, with no critical bugs open

- Platform uptime of 99% or higher after launch

- Learner satisfaction of 4 out of 5 or higher in the post-launch survey