## Schedule
Task ID | Phase | Task | Owner | Dependencies | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Schedule Variance (days) | Status | % Complete
T01 | Initiation | Define project objectives | Project Manager |  | 2026-06-01 | 2026-06-04 | 2026-06-01 | 2026-06-04 | 3 | 3 | 0 | Completed | 100
T02 | Initiation | Draft project charter | Project Manager | 1 | 2026-06-04 | 2026-06-08 | 2026-06-04 | 2026-06-09 | 4 | 5 | 1 | Completed | 100
T03 | Initiation | Identify stakeholders | Project Manager | 1 | 2026-06-04 | 2026-06-07 | 2026-06-04 | 2026-06-07 | 3 | 3 | 0 | Completed | 100
T04 | Initiation | Secure budget approval | Sponsor | 2 | 2026-06-08 | 2026-06-12 | 2026-06-08 | 2026-06-12 | 4 | 4 | 0 | Completed | 100
T05 | Initiation | Project kick-off meeting | Project Manager | 4 | 2026-06-12 | 2026-06-13 | 2026-06-12 | 2026-06-13 | 1 | 1 | 0 | Completed | 100
T06 | Research | Competitor analysis | Marketing Lead | 5 | 2026-06-13 | 2026-06-19 | 2026-06-14 | 2026-06-20 | 6 | 6 | 1 | Completed | 100
T07 | Research | Student survey design | Marketing Lead | 5 | 2026-06-13 | 2026-06-17 | 2026-06-13 | 2026-06-17 | 4 | 4 | 0 | Completed | 100
T08 | Research | Run student survey | Marketing Lead | 7 | 2026-06-17 | 2026-06-24 | 2026-06-18 | 2026-06-27 | 7 | 9 | 3 | Completed | 100
T09 | Research | Analyze survey results | Content Lead | 8 | 2026-06-24 | 2026-06-28 | 2026-06-24 | 2026-06-28 | 4 | 4 | 0 | Completed | 100
T10 | Research | Finalize course catalogue | Content Lead | 9 | 2026-06-28 | 2026-07-02 | 2026-06-28 | 2026-07-01 | 4 | 3 | -1 | Completed | 100
T11 | Content | Hire instructors | Content Lead | 5 | 2026-06-15 | 2026-06-23 | 2026-06-15 | 2026-06-25 | 8 | 10 | 2 | Completed | 100
T12 | Content | Create course outlines | Content Lead | 11 | 2026-06-23 | 2026-06-29 | 2026-06-25 | 2026-07-01 | 6 | 6 | 2 | Completed | 100
T13 | Content | Record video lessons - batch 1 | Instructors | 12 | 2026-06-29 | 2026-07-09 | 2026-07-01 | 2026-07-14 | 10 | 13 | 5 | Completed | 100
T14 | Content | Record video lessons - batch 2 | Instructors | 13 | 2026-07-09 | 2026-07-17 | 2026-07-12 | 2026-07-22 | 8 | 10 | 5 | Completed | 100
T15 | Content | Create quizzes and assignments | Content Lead | 12 | 2026-07-05 | 2026-07-13 | 2026-07-05 | 2026-07-13 | 8 | 8 | 0 | Completed | 100
T16 | Content | Content quality review | QA Analyst | 14,15 | 2026-07-17 | 2026-07-22 | 2026-07-17 | 2026-07-22 | 5 | 5 | 0 | Completed | 100
T17 | Platform setup | Select LMS vendor | Tech Lead | 5 | 2026-06-15 | 2026-06-22 | 2026-06-14 | 2026-06-21 | 7 | 7 | -1 | Completed | 100
T18 | Platform setup | Configure platform | Tech Lead | 17 | 2026-06-22 | 2026-07-02 | 2026-06-22 | 2026-07-02 | 10 | 10 | 0 | Completed | 100
T19 | Platform setup | Payment gateway integration | Tech Lead | 18 | 2026-07-02 | 2026-07-09 | 2026-07-02 | 2026-07-13 | 7 | 11 | 4 | Completed | 100
T20 | Platform setup | Build onboarding flow | Tech Lead | 18 | 2026-07-09 | 2026-07-16 | 2026-07-09 | 2026-07-16 | 7 | 7 | 0 | Completed | 100
T21 | Platform setup | User acceptance testing | QA Analyst | 19,20 | 2026-07-16 | 2026-07-21 | 2026-07-18 | 2026-07-26 | 5 | 8 | 5 | Completed | 100
T22 | Platform setup | Fix defects | Tech Lead | 21 | 2026-07-21 | 2026-07-25 | 2026-07-24 | 2026-07-29 | 4 | 5 | 4 | Completed | 100
T23 | Marketing | Marketing strategy | Marketing Lead | 10 | 2026-06-25 | 2026-06-30 | 2026-06-25 | 2026-06-30 | 5 | 5 | 0 | Completed | 100
T24 | Marketing | Create brand assets | Marketing Lead | 23 | 2026-06-30 | 2026-07-07 | 2026-06-30 | 2026-07-07 | 7 | 7 | 0 | Completed | 100
T25 | Marketing | Build landing page | Marketing Lead | 24 | 2026-07-07 | 2026-07-15 | 2026-07-07 | 2026-07-15 | 8 | 8 | 0 | Completed | 100
T26 | Marketing | Social media campaign | Marketing Lead | 24 | 2026-07-13 | 2026-07-27 | 2026-07-13 | 2026-07-29 | 14 | 16 | 2 | Completed | 100
T27 | Marketing | College partnership outreach | Marketing Lead | 23 | 2026-07-06 | 2026-07-20 | 2026-07-06 | 2026-07-20 | 14 | 14 | 0 | Completed | 100
T28 | Marketing | Referral program setup | Marketing Lead | 25 | 2026-07-16 | 2026-07-23 | 2026-07-16 | 2026-07-23 | 7 | 7 | 0 | Completed | 100
T29 | Launch | Go-live checklist | Project Manager | 16,22 | 2026-07-23 | 2026-07-26 | 2026-07-26 | 2026-07-30 | 3 | 4 | 4 | Completed | 100
T30 | Launch | Soft launch (beta users) | Project Manager | 29 | 2026-07-25 | 2026-07-27 | 2026-07-28 | 2026-07-31 | 2 | 3 | 4 | Completed | 100
T31 | Launch | Public launch | Project Manager | 30 | 2026-07-27 | 2026-07-28 | 2026-07-30 | 2026-07-31 | 1 | 1 | 3 | Completed | 100
T32 | Launch | Launch week support | Tech Lead | 31 | 2026-07-27 | 2026-08-01 | 2026-07-30 | 2026-08-04 | 5 | 5 | 3 | Completed | 100
T33 | Review | Collect user feedback | Marketing Lead | 31 | 2026-08-02 | 2026-08-12 | 2026-08-05 | 2026-08-17 | 10 | 12 | 5 | Completed | 100
T34 | Review | Performance review | Project Manager | 33 | 2026-08-12 | 2026-08-18 | 2026-08-15 | 2026-08-24 | 6 | 9 | 6 | Completed | 100
T35 | Review | Lessons learned and closure | Project Manager | 34 | 2026-08-18 | 2026-08-23 | 2026-08-23 |  | 5 |  |  | In Progress | 50

## RACI
Task ID | Task | Project Manager | Sponsor | Content Lead | Tech Lead | Marketing Lead | Instructors | QA Analyst
T01 | Define project objectives | R | A | C | C | C | I | I
T02 | Draft project charter | R | A | C | C | C | I | I
T03 | Identify stakeholders | R | A | C | C | C | I | I
T04 | Secure budget approval | R | A | C | C | C | I | I
T05 | Project kick-off meeting | R | A | C | C | C | I | I
T06 | Competitor analysis | A | I | R | I | R | C | I
T07 | Student survey design | A | I | R | I | R | C | I
T08 | Run student survey | A | I | R | I | R | C | I
T09 | Analyze survey results | A | I | R | I | R | C | I
T10 | Finalize course catalogue | A | I | R | I | R | C | I
T11 | Hire instructors | A | I | R | I | I | R | C
T12 | Create course outlines | A | I | R | I | I | R | C
T13 | Record video lessons - batch 1 | A | I | R | I | I | R | C
T14 | Record video lessons - batch 2 | A | I | R | I | I | R | C
T15 | Create quizzes and assignments | A | I | R | I | I | R | C
T16 | Content quality review | A | I | R | I | I | R | C
T17 | Select LMS vendor | A | I | C | R | I | C | C
T18 | Configure platform | A | I | C | R | I | C | C
T19 | Payment gateway integration | A | I | C | R | I | C | C
T20 | Build onboarding flow | A | I | C | R | I | C | C
T21 | User acceptance testing | A | I | C | R | I | C | C
T22 | Fix defects | A | I | C | R | I | C | C
T23 | Marketing strategy | A | C | C | C | R | I | I
T24 | Create brand assets | A | C | C | C | R | I | I
T25 | Build landing page | A | C | C | C | R | I | I
T26 | Social media campaign | A | C | C | C | R | I | I
T27 | College partnership outreach | A | C | C | C | R | I | I
T28 | Referral program setup | A | C | C | C | R | I | I
T29 | Go-live checklist | A | C | R | R | R | I | C
T30 | Soft launch (beta users) | A | C | R | R | R | I | C
T31 | Public launch | A | C | R | R | R | I | C
T32 | Launch week support | A | C | R | R | R | I | C
T33 | Collect user feedback | R | A | C | C | C | I | I
T34 | Performance review | R | A | C | C | C | I | I
T35 | Lessons learned and closure | R | A | C | C | C | I | I

## Budget
Category | Planned Cost (INR) | Actual Cost (INR) | Variance (INR)
Instructors and content | 240000 | 262000 | 22000
Platform and tools | 160000 | 155000 | -5000
Marketing | 200000 | 218000 | 18000
Team and project management | 100000 | 96000 | -4000
Contingency reserve | 100000 | 35000 | -65000

## Marketing_Spend
Week | Planned Spend (INR) | Actual Spend (INR)
6 | 20000 | 15000
7 | 25000 | 20000
8 | 30000 | 25000
9 | 35000 | 40000
10 | 35000 | 45000
11 | 30000 | 40000
12 | 25000 | 33000

## Risks
Risk ID | Risk | Category | Probability (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status
R01 | Instructors hired late | Schedule | 3 | 4 | 12 | Start hiring early; keep 2 backup candidates | Content Lead | Occurred
R02 | Video content quality below standard | Quality | 3 | 4 | 12 | Review checklist and pilot lesson before batch recording | QA Analyst | Mitigated
R03 | Payment gateway integration fails | Technical | 2 | 5 | 10 | Test in sandbox early; shortlist a backup provider | Tech Lead | Occurred
R04 | Platform downtime at launch | Technical | 2 | 5 | 10 | Load test and a soft launch with beta users | Tech Lead | Mitigated
R05 | Marketing spend overruns | Budget | 3 | 3 | 9 | Weekly spend review; pause low-ROI channels | Marketing Lead | Occurred
R06 | Low sign-ups from social media | Market | 3 | 4 | 12 | Add college partnerships and a referral program | Marketing Lead | Mitigated
R07 | Scope creep from new feature requests | Scope | 4 | 3 | 12 | Change control: sponsor approval for any addition | Project Manager | Open
R08 | Key team member unavailable | Resource | 2 | 4 | 8 | Cross-train; document tasks; maintain a RACI | Project Manager | Open
R09 | Low course completion rates | Market | 3 | 3 | 9 | Add quizzes, reminders and certificates | Content Lead | Open
R10 | Data privacy or compliance issue | Legal | 2 | 5 | 10 | Privacy policy review; collect minimum student data | Sponsor | Mitigated
R11 | Competitor launches a cheaper offer | Market | 3 | 3 | 9 | Early-bird pricing; differentiate on mentor support | Marketing Lead | Open
R12 | Sponsor delays budget approval | Budget | 2 | 4 | 8 | Pre-brief sponsor; submit a clear business case | Project Manager | Closed

## Targets
Week | Target Sign-ups (scaled sample)
9 | 80
10 | 90
11 | 90
12 | 90